## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | TalkIt
Project Manager | Dan.Badris
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Testing Phase | Defect Description | Lifecycle Phase | Priority | Severity | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | Severity | PM | Lifecycle Phase
1 | 02-20-019 | Priti | Unit Testing | Messages are duplicately posted | Development | Meduim | Low | Priti | 02-20-2019 | 02-22-2019 | Closed | NA | 02-22-2019 |  | this is happeing due to the local server installation and testing.. it wont be occur in production | New

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Testing Phase | Choose the testing phase defect was encountered: Unit testing,System Testing
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
C = Critical (Tremendous, the whole application won’t work unless it is resolved) should be fixed immediately.
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Severity | The Severity denotes the implication of the defect on the project performance
C = Critical / Show Stopper (A defect that completely hampers or blocks testing of the product or any feature. To be solved immediately)
H = Major / High (functionalities are running grossly away from the expectations or not doing what it supposed to)
M = Moderate / Normal (A product or application doesn’t meet certain criteria or exhibits some abnormal behavior, but the entire functionality is still working fine)
L = Minor / Low (A bug does not have any impact on the functionality but it is still a valid defect and should be tackled)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).

## Test Cases
Test Type | Test case ID | New or old | Product | Test items: (what do you test ) | Test priority (high/medium/low) | Dependencies (to other test case/requirement if any): | Test steps: | Expected output | Actual output: | Pass or Fail: | Bug id/link: | Additional notes
Manual | 1.1.1 | Old |  | Create User | Low | Environment should be activated | 1. Open the URL: http://3blueprints.com/signin?next=/communication/ 2. Click on "I want to Register" or "Sign Up" in the screen upper right corner 3. Enter the input detailes 2. Click "Register" | Registration Complete! | Registration Complete! | Pass | NA
Manual | 1.2.1 | Fix |  | Create Chat Team | Low | User is logged in | 1. New Team name is empty 2. Save | Empty Team Name should not be accepted | Empty Team Name accepted | Failed | 3
Manual | 1.2.2 | Fix |  | Create Chat Team | Low | User is logged in | 1.Create New Team 2. Enter Team Name 3. Save | New Team is created |  | Pass | 3
Manual | 1.3.1 | Old |  | Text Chat | High | User is logged in | 1. Place the Cursor in the message typing field 2. Enter or click Send Message Icon | Other Chat room Participants receive the message | Other Chat room Participants receive the message | Pass | NA
Manual | 1.4.1 | New |  | Video Chatting | High | User is logged in | Click on the Video Chat Icon | Video Chat screen appears on the chat room Camera is started | Video Chat screen appears on the chat room Camera is started | Pass | NA
Manual | 1.5.1 | New |  | File Sharing via Google Doc -Upload | High | user is logged in the Communication tool Chat room | 1. Click Google Drive Icon 2. Select Upload File from the menu 3. Sign in to google account 4. Click on "Select File" 5. Brows Then select file from the local drives 6. Upload | File is uploaded and shared via google Drive | File has been uploaded and shared via google Drive | Pass | NA
Manual | 1.5.2 | New |  | File Sharing via Google Doc -Download | High | user is logged in the Communication tool Chat room | 1. Click Google Drive Icon 2. Select Download File from the menu 3. Sign in to google account 4. Select a specifc File to be downloaded then Enter | File is downloaded from google Drive | File has been downloaded from google Drive | Pass | NA
Manual | 1.1 | New | Chatting tool | Message duplication | High | user is logged in the Communication tool Chat room | 1. Log in to chat Room 2. send text message | only one copy of the message to be sent over the chat room | sent message received twice | Pass | 3
Manual | 1.11.1 | New |  | Change password | Meduim | user is logged in the Communication tool Chat room | 1. From the upper right corner, Click on the user name 2. From the Drop down menue select "Change Password" 3. Enter old/New password 2.Click "Confirm Change & Logout" | Password is changed successfully | Password has been changed successfully | Pass
Selenium Test |  | New |  | Upload file to chat room via Google Drive | high
Selenium Test |  | New |  | Download file to chat room via Google Drive | high
Selenium Test |  | New |  | Check video chat funcionality | high
Selenium Test |  | Old |  | User login to communication page | high
Selenium Test |  | Old |  | Create chat team | medium |  | 1.Login user 2.Click "Create New Teams " button 3.Add team name 4.Click "save" button 5.Check whether new team is created | the new team name will show in"Chatting Room" list | Same as expected | Pass
Selenium Test |  | New |  | Edit Team Name | low |  | 1.Login user 2.Click "Create New Teams " button 3.Add team name 4.Click "save" button 5.Click "Options" button and than "Edit Team" 6.Edit team name 7.Check whether team name is edited | the edited team name will show in "Chatting Room" list | Same as expected | Pass
Selenium Test |  | New |  | Check system accept to unsanitized message to chat room | high |  | 1.Enter a created team 2.Send a message which is unsanitized like Html code to this team 3.Check is message rendered as text | message will show in message list as a text | Same as expected | Pass
Selenium Test |  | Old |  | Dialog between two user in the chat room | high |  | 1.First user enter a created team 2.Send a message to this team 3.Second user also sent a message to this team 4.Check whether messages is sent and users can see both messages | both messages will show in message list in the same team | Same as expected | Pass