## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | TalkIt
Project Manager | Dan.Badris
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Testing Phase | Defect Description | Lifecycle Phase | Priority | Severity | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | Severity | PM | Lifecycle Phase
1 | 02-20-019 | Priti | Unit Testing | Messages are duplicately posted | Development | Meduim | Low | Priti | 02-20-2019 | 02-22-2019 | Closed | NA | 02-22-2019 |  | this is happeing due to the local server installation and testing.. it wont be occur in production | New

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Testing Phase | Choose the testing phase defect was encountered: Unit testing,System Testing
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
C = Critical (Tremendous, the whole application won’t work unless it is resolved) should be fixed immediately.
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Severity | The Severity denotes the implication of the defect on the project performance
C = Critical / Show Stopper (A defect that completely hampers or blocks testing of the product or any feature. To be solved immediately)
H = Major / High (functionalities are running grossly away from the expectations or not doing what it supposed to)
M = Moderate / Normal (A product or application doesn’t meet certain criteria or exhibits some abnormal behavior, but the entire functionality is still working fine)
L = Minor / Low (A bug does not have any impact on the functionality but it is still a valid defect and should be tackled)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).

## Test Cases
Test Type | Test case ID | New or old | Product | Test items: (what do you test ) | Test priority (high/medium/low) | Dependencies (to other test case/requirement if any): | Test steps: | Expected output | Actual output: | Pass or Fail: | Bug id/link: | Additional notes
Python unittest | 1.1 | New | Application Backend-- | app/api_module/user_controllers.py | high | None | Login through admin user id Test for user login with valid user credential Test for user login with invalid user credential Create a new user :test@email.com Test new user is an instance of User class Test to get new user created: - Login through new username and password created - Get the user id from the login response (the token contains the id) - Retreive more information about the user with his id. | - Login with valid creadential returns a status code of 200. - Login with invalid creadential returns a status code of 401 - New user "test@email.com" gets created - New user is an instance of User class - Get the new user id created |  | Pass | None
Python unittest | 1.1 | New | Application Backend--test_role_controller | app/api_module/test_role_controller.py | medium | User | Login through admin user id and get valid token Test to create new role by admin account Test to create new role by non-admin account Test to get all roles information by admin account Test to get all roles information by non-admin account | Successfully get admin user token New role gets created by admin account successfully New role won't be created by non-admin account and gets hint "Cannot perform that function!" All roles information will successfully be displayed by admin account Non-admin won't be able to get all roles information by hint "Cannot perform that function!" |  | Pass | None
Python unittest | 1.1 | New | Application Backend--test_sprint_controller | app/api_module/test_sprint_controller.py | medium | Company Project | Get admin token first Test to create new sprint by admin ID Test to get all sprints by admin account | Successfully get the token Sucessfully create new sprint by admin ID Successfullly get all information by admin account |  | Pass | None | Some probems with Sprint that only one project can only have one sprint.