## Test Cases for Issue and Chat
Test Type | Test case ID | New or old | Product | Test items: (what do you test ) | Test priority (high/medium/low) | Dependencies (to other test case/requirement if any): | Test steps: | Expected output | Actual output: | Pass or Fail: | Bug id/link: | Additional notes
SIT | 1.1 | New | Team2-PMP Web App | User Login | High | A valid user account | -Launch application : https://cyrilfotso.github.io/pmp-frontend/login - Enter correct username and password and hit login button | Home Page | Launch successful Launches Issue Page rather than Home Page | Fail | https://cyrilfotso.github.io/pmp-frontend/issues
SIT | 1.2 | New | Team2-PMP Web App | User Sign-Up | High |  | -Launch application : https://cyrilfotso.github.io/pmp-frontend/login - Hit Sign-In button - Enter user details : name,email-id,password,skills,profile - Hit Submit button - Enter new username and password and hit login button | Login Successful with new user-id and password | Home Page Launch successful | Pass
SIT | 1.3 | New | Team2-PMP Web App | User Login- Check for empty validation | medium |  | -Launch application : https://cyrilfotso.github.io/pmp-frontend/login - Hit Login button without entering username and password | Page should display "Usename is required" and "Password is required" | Page displayed "Usename is required" and "Password is required" | Pass
SIT | 1.4 | New | Team2-PMP Web App | Issue Component - Open Issues Page | High |  | - Login to web application - Hit on Issues button on menu bar | Display issues page | Issue Page displayed | Pass
SIT | 1.5 | New | Team2-PMP Web App | Issue Component - Create a new issue | High |  | - Hit Issues button on menu bar - Click on add an issue - Enter Issue details: Issue title, start/end date, priority, project, user - Click on Create Issue button | New issue created and displayed under input queue | New issue created and displayed under input queue | Pass
SIT | 1.6 | New | Team2-PMP Web App | Issue Component - Change issue status | High |  | - Hit Issues button on menu bar - Drag and drop an issue from one status to another | Issue displayed under new issue status | Need to refresh the page for issue to be displayed under new status | Fail | https://cyrilfotso.github.io/pmp-frontend/issues
SIT | 1.7 | New | Team2-PMP Web App | Issue Component - Update Issue Comment | High |  | - Click on issue title - Write issue comments and then click on add button | Pop-up message appears saying "Comment has been added successfully" Click on issue and comment should be displayed with user name and date | Pop-up message appears saying "Comment has been added successfully" Click on issue and comment should be displayed with user name and date | Pass
SIT | 1.8 | New | Team2-PMP Web App | Issue Component - Edit Issue details ( For example end date) | medium |  | - Click on issue edit button - Update the details - Click on Save button | Issue should display updated details | Issue displayed updated details | Pass
SIT | 1.7 | New | Team2-PMP Web App | Issue Component - Delete and issue | medium |  | - Click on issue delete button - A pop-up appears for delete confirmation, click on OK button | Issue disappears from status queue | Issue disappeared from status queue | Pass
SIT | 1.8 | New | Team2-PMP Web App | Issue Component - frontend scripts | medium |  | - Execute karma.js script in pmp-frontend/src/app folder through ng test | All default test cases should pass | IssuesComponent ; FAILED Can't bind to ngModel; since it isn't a known property of input. | Fail | https://cyrilfotso.github.io/pmp-frontend/issues
SIT | 1.8 | New | Team3-PMP Web App | Chat Componenent - Text message sending | medium |  | - type and send a piece text to the group chat room | The text is properly displayed in the chat room with time below. | text is displayed in the chat room as expected | Pass
SIT | 1.9 | New | Team4-PMP Web App | Chat Componenent - self draw message sending | medium |  | - draw a emoji at drawing section and send it to the group chat room | The drawing is properly displayed in the chat room with time below. | The drawing is displayed in the chat room as expected | Pass
SIT | 2 | New | Team5-PMP Web App | Chat Componenent - emoji message sending | medium |  | - select a emoji from the emoji tab and send it to the group chat room | The emoji is properly displayed in the chat room with time below. | ???????? is dispalyed in the chatroom instead of a emoji. | Fail | https://cyrilfotso.github.io/pmp-frontend/issues
SIT | 2.1 | NEW | Team2-PMP Web App | Chat function for direct channels----create new direct channel to specific person | High |  | 1.click the "NEW direct channel" botton 2.choose someone want to chat in the list 3. click "ok" botton to create new direct channel | 1. The message that new direct channel was created 2. The new direct channel was listed on the left of website | 1. The message that new direct channel was created 2. The new direct channel was listed on the left of website | Pass |  | Unstable, sometimes need to refresh the page
SIT | 2.2 | NEW | Team2-PMP Web App | Chat function for direct channels----open direct messages to someone | High |  | 1. double click the name on direct channel | 1. new chat window with selected person | 1. new chat window with selected person | Pass
SIT | 2.3 | NEW | Team2-PMP Web App | Chat function for direct channels----send direct messages to someone | High |  | 1. double click on the bottom of selected direct channel 2. type message "Hello" 3. click "send" botton | 1. the message "Hello" will display in the channel content | 1. the message "Hello" will display in the channel content | Pass
SIT | 2.4 | NEW | Team2-PMP Web App | Chat function for direct channels----send direct emoji to someone | High |  | 1. double click on the bottom of selected channel 2. click emoji botton 3. select any one of emojis 4. click "send" botton | 1. to see the emoji in the channel content | 1. only see "????" in the channel content | fail | https://cyrilfotso.github.io/pmp-frontend/issues
SIT | 2.5 | NEW | Team2-PMP Web App | Chat function for direct channels----send DIY picture to someone | Medium |  | 1. select color in the color selection 2. use mice to draw in the blank 3. click "send" botton | 1. to see the drawing picture in the channel content | 1. to see the drawing picture in the channel content | Pass |  | The picture can display successful after refresh the page.

## Test Cases for Task Component
Test Type | Test case ID | New or old | Product | Test items: (what do you test ) | Test priority (high/medium/low) | Dependencies (to other test case/requirement if any): | Test steps: | Expected output | Actual output: | Pass or Fail: | Bug id/link: | Additional notes
SIT | 2.1 | New | Team2-PMP Web App | Task Component - Display Task Management Page | High |  | - Login to web application - Click "Tasks" button on menu bar | Display tasks page | tasks page displayed correctly | pass
SIT | 2.2 | New | Team2-PMP Web App | Task Component - Create a new sprint | High | A valid project | - Click "+ New Sprint" button on the left side bar - Enter Sprint Name Start Date Due Date Select Project Select Teams - Click "Create New" | New sprint created and displayed on the left side bar | New sprint created and displayed on the left side bar | pass
SIT | 2.3 | New | Team2-PMP Web App | Task Component - Update a sprint | High |  | - Click the edit button on the left side bar - Change Sprint Name Start Date Due Date - Click "save" | Sprint updated (Click the edit button again to confirm the chage) | Update confirmed | pass
SIT | 2.4 | New | Team2-PMP Web App | Task Component - Create a new task | High |  | - Click "+" button on the left side bar (beside each sprint) - Fill in the following information Task Name Start Date Due Date Priority Level Select Sprint Assign to user - Click "Create New" | New task created and displayed on the right side | New task created and displayed on the right side | pass
SIT | 2.5 | New | Team2-PMP Web App | Task Component - Update a task | High |  | - Click the edit button on one specific task - Change Task Name Start Date Due Date Priority Level Select Sprint Assign to user - Click "save" | Task updated (Click the edit button again to confirm the chage) | Update confirmed | pass
SIT | 2.6 | New | Team2-PMP Web App | Task Component - Delete a task | High |  | - Click the delete button on one specific task - Click "ok" | Task deleted | Task deleted | pass
SIT | 2.7 | New | Team2-PMP Web App | Task Component - Change task status | High |  | - Drag and drop a task to another status column | Task is changed to another status | Task is changed to another status but has to refresh the web page | partially fail
SIT | 2.8 | New | Team2-PMP Web App | Task Component - Change task priority | High |  | - Click the edit button on one specific task - Change Priority Level - Click "save" | Priority being displayed changes correctly | Priority being displayed changed | pass
SIT | 2.9 | New | Team2-PMP Web App | Task Component - Change task deadline | High |  | - Click the edit button on one specific task - Change Due Date - Click "save" | Deadline being displayed changes correctly | Deadline being displayed changed | pass
SIT | 2.10 | New | Team2-PMP Web App | Task Component - Reassign a task to another team member | High |  | - Click the edit button on one specific task - Change Assign to user - Click "save" | User being displayed changes correctly | User being displayed changed and the task status also changed automatically to Input Queue | partially fail
SIT | 2.11 | New | Team2-PMP Web App | Task Component - Comment on task | High |  | - Click the link on one specific task - Enter comments - Click "Add" | Comments to be displayed | Comments were displayed | pass
SIT | 2.12 | New | Team2-PMP Web App | Task Component - Hold an task | High |  |  |  |  | Not done yet
SIT | 2.13 | New | Team2-PMP Web App | Task Component - Filter an task by user | High |  | - Enter a keyword in the "user filter" field | Tasks with user containing the keyword to be displayed | Tasks with user containing the keyword were displayed | pass
SIT | 2.14 | New | Team2-PMP Web App | Task Component - Filter an task by project | High |  | - Enter a keyword in the "project filter" field | Tasks with project containing the keyword to be displayed | Tasks with project containing the keyword were displayed | pass
SIT | 2.15 | New | Team2-PMP Web App | Task Component - Filter an task by sprint | High |  | - Enter a keyword in the "sprint filter" field | Tasks with sprint containing the keyword to be displayed | Tasks with sprint containing the keyword were displayed | pass
SIT | 2.16 | New | Team2-PMP Web App | Task Component - Reset a filter by clicking the reset icon | High |  |  |  |  | Not done yet
SIT | 2.17 | New | Team2-PMP Web App | Task Component - Zoom in and out | High |  | - Zoom in and zoom out randomly on the task management page | Display of tasks do not crush | Contents stayed in their frame | pass
SIT | 2.18 | New | Team2-PMP Web App | Task Component - Go to home page | High |  | - Click "Home" button on menu bar | Display Home page | Home page displayed | pass
SIT | 2.19 | New | Team2-PMP Web App | Task Component - Go to Issues page | High |  | - Click "Issue" button on menu bar | Display Issue page | Issue page displayed | pass
SIT | 2.20 | New | Team2-PMP Web App | Task Component - Go to Chat room | High |  | - Click "Chat" button on menu bar | Display Chat page | Chat page displayed | pass
SIT | 2.21 | New | Team2-PMP Web App | Task Component - Go to Management page | High |  | - Click "Manage - Companies" button on menu bar - Click "Manage - Projects" button on menu bar - Click "Manage - Teams" button on menu bar - Click "Manage - Employees" button on menu bar - Click "Manage - Roles Management" button on menu bar | Display corresponding page | Corresponding page displayed | pass